# M1 Audit Pack — Polestar Advisory Workbench

Document version: 1.0 (Word export)
Milestone: M1 — Live baseline audit and locked priority order
Date: 8 July 2026
Auditor: Tommy To
Production URL: https://document-asset-manager-stioffain29.replit.app/
Scope: Audit and plan only — no code fixes in M1

Basis: Dev-led audit — codebase review, unauthenticated production API probes (8 Jul 2026), prior workbench audit (docs/workbench-audit-2026-06-17.md), and in-repo PDF/font audit artifacts (docs/m1-evidence/). No joint live walkthrough required. Owner may correct any row during M2 if secrets have changed.

Evidence bundle: Attach or store alongside this document: docs/m1-evidence/ (screenshots, sample PDF, font audit log).

## Executive summary

| Area | Rating | One-line verdict |
| --- | --- | --- |
| Overall | AMBER | Usable foundation; commercially incomplete without workflow, PDF polish, and distribution |
| Live app stability | AMBER | Core pipeline works; optional integrations and admin controls need triage |
| Source Health accuracy | AMBER | Unified integration status exists; optional rows classified below |
| Report / PDF quality | AMBER | Strong templates; not consistently customer-demo ready |
| Workflow | RED vs Phase 2 | Thin pipeline (draft / review / published); no approval gates or distribution |
| Distribution | Not built | Correctly deferred to M6 |
| Engineering quality | GREEN | 80+ tests, typecheck clean, contract-first API |

Recommendation: Sign off M2 stabilisation backlog, then fund M3, then M4, then M5, then M6 in that order (see Appendix A).

## Action responsibility (M1 evidence vs M2 delivery)

| Who | Responsibility | When |
| --- | --- | --- |
| Owner | Sign Appendix C; confirm integration decisions still match production secrets; provision keys/approvals if turning integrations on | M1 sign-off and ongoing |
| Dev | Complete this audit pack with code/probe/repo evidence; deliver M2 backlog | M1 now; M2 after sign-off |
| Owner + Dev | Owner sets environment; dev ensures Source Health UI matches truth table (Appendix B items B1–B4) | M2 must-fix |

Owner actions at sign-off (confirm, not collect)

- Review Section 2.2 classifications; flag any row where production secrets differ from this audit.

- Sign Appendix C to lock M3–M6 priority order and M2 backlog.

- Optional later: provision ReliefWeb, Liveuamap whitelist, OpenAI, or GDELT if the product needs them.

Dev actions (M2 — after M1 locked)

- Appendix B items B5–B10: route reliability, error states, integration status tests, smoke PDF path.

- Appendix B items B1–B4: align Source Health UI with classifications below.

- M3+ workflow, PDF polish (M4), distribution (M6) per locked priority order.

Contents

M1 Audit Pack — Polestar Advisory Workbench	1

Executive summary	1

Action responsibility (M1 evidence vs M2 delivery)	2

1. Live app checklist	4

1.1 Core pages	4

1.2 Auth and access	5

1.3 Ingest scheduler (production)	5

1.4 Performance spot-check	6

2. Source Health truth table	7

2.1 Core data feeds (RSS and prices — required for product)	7

2.2 Optional external integrations	7

2.3 Source Health UI honesty (M2 target)	9

3. Report quality scorecard	10

3.1 Scorecard	10

3.2 Cross-cutting PDF issues (code review)	10

3.3 Map tool (UI, not PDF)	11

4. Workflow gap map	12

4.1 Today (as built)	12

4.2 Target (M3 requirements)	12

4.3 Explicitly deferred (not M3)	12

4.4 Workflow comparison (today vs target)	13

5. Risk register	14

6. Engineering baseline (context only — not M1 acceptance)	16

Appendix A — Priority order for M3–M6 (locked)	17

Appendix B — M2 fix backlog (numbered, for sign-off)	18

Appendix C — Owner sign-off	20

C.1 M1 Audit Pack acceptance	20

C.2 Sign-off	20

Appendix D — Evidence index	21

## 1. Live app checklist

Core routes assessed by dev audit: route inventory, June 2026 workbench audit (live data, end-to-end report to PDF), production URL, and one in-repo production screenshot.

Verification legend

| Symbol | Meaning |
| --- | --- |
| Yes (Code) | Confirmed in repository |
| Yes (Prod) | Unauthenticated production probe |
| Yes (Dev audit) | Prior audit plus route/code review |
| No | Not independently verified on production UI |

### 1.1 Core pages

| # | Route | Purpose | Load OK? | Empty/error states OK? | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | / | Dashboard, KPIs, topic cards, recent incidents | Yes (Dev audit) | Yes (Dev audit) | Not a command centre — no report pipeline or attention queue |
| 2 | /incidents | Incident list and filters | Yes (Dev audit) | Yes (Dev audit) | API listIncidents capped at 365 days |
| 3 | /map | Incident map and optional Liveuamap overlay | Yes (Dev audit) | No | Overlay empty when Liveuamap upstream blocks IP (Section 2.2) |
| 4 | /reports | Report list | Yes (Dev audit) | Yes (Dev audit) | Filter by topic/status only; no owner, due date, or pipeline view |
| 5 | /reports/:id | Report editor, preview, PDF | Yes (Dev audit) | Yes (Dev audit) | PDF export not gated by approval status |
| 6 | /sources | Source Health and integrations panel | Yes (Dev audit) | Yes (Dev audit) | Admin token required for source mutations |
| 7 | /countries | Country report index | Yes (Dev audit) | Yes (Dev audit) |  |
| 8 | /countries/:slug | Country report builder | Yes (Dev audit) | Yes (Dev audit) | Per-country pages partly code-driven |
| 9 | /topics/shipping | Shipping monitor | Yes (Dev audit) | Yes (Dev audit) |  |
| 10 | /topics/cargo-watch | Cargo Watch monitor | Yes (Dev audit) | Yes (Dev audit) |  |
| 11 | /calendar | Publication calendar | Yes (Dev audit) | Yes (Dev audit) | Read-only cadence display |
| 12 | /spot-reports | Spot reports | Yes (Dev audit) | Yes (Dev audit) | Owner session only (no admin token) |

Evidence references (Section 1.1): June 2026 workbench audit Section A; production screenshot E1 (Appendix D); country PDF sample Section 3.1.

### 1.2 Auth and access

| Check | Expected | Verified? | Evidence |
| --- | --- | --- | --- |
| Unauthenticated user blocked from data routes | 401 or login redirect | Yes (Code), Yes (Prod) | requireOwner on data routers; GET /api/incidents returned 401 on 8 Jul 2026 |
| Non-owner Replit account blocked | 403 | Yes (Code) | requireOwner returns 403 when authenticated but not owner; not re-tested with second account |
| GET /api/healthz public | 200 | Yes (Prod) | 200 with body {"status":"ok"} on 8 Jul 2026 |
| GET /api/access returns authenticated and allowed flags | 200 | Yes (Prod) | 200 with {"authenticated":false,"allowed":false} when logged out |

### 1.3 Ingest scheduler (production)

| Check | Expected | Verified? | Evidence |
| --- | --- | --- | --- |
| Scheduler enabled (INGEST_SCHEDULE_ENABLED is not false) | Boot and recurring ingest | Yes (Code), Yes (Dev audit) | Default on when unset; June audit boot log shows scheduler start |
| Stale data triggers boot catch-up | Refresh when older than INGEST_INTERVAL_HOURS (default 12h) | Yes (Code), Yes (Dev audit) | June audit confirms live prices |
| Ingest failures visible (not silent) | WARN logs and Source Health degradation | Yes (Code) | summarizeIngestFailures and recordSourceHealth; June boot hadFailures: false |
| Manual ingest POST /api/admin/ingest | 503 if no token; 401 if wrong token; 200 if token set | Yes (Code), Yes (Prod) | Prod: no token returned 401 (token is configured) on 8 Jul 2026 |

### 1.4 Performance spot-check

| Check | Observation | Pass? |
| --- | --- | --- |
| Dashboard incident fetch bounded | Fetches max 1-year window, not full table | Yes (Code) — API caps days at 365 |
| Core pages load in under 5s on production | Not timed in this audit | No — defer to M2 item B8 if slow |
| PDF generation completes without timeout | Country and topic reports export via headless builders | Yes (Dev audit) — font audit PASS; see Appendix D E3 and E4 |

## 2. Source Health truth table

Classification key (M1 acceptance)

| Classification | Meaning |
| --- | --- |
| Working | Configured and producing useful output |
| Intentionally off | Deliberately disabled or not provisioned; UI should say so clearly |
| Broken | Configured but failing; needs fix or owner action |
| Pending | Built but awaiting external approval (e.g. ReliefWeb appname) |

### 2.1 Core data feeds (RSS and prices — required for product)

| Source | Purpose | Classification | Action owner | Notes |
| --- | --- | --- | --- | --- |
| Google News RSS | Discovery for all topic feeds | Working | — | June audit: live, data fresh |
| FRED | Brent, WTI, jet fuel | Working | — | No API key required |
| Yahoo Finance | Crude close (FRED fallback) | Working | Dev | Public endpoint; reliability risk if shape changes |
| World Bank Pink Sheet | Fertiliser prices | Working | — |  |
| Google News URL resolution | De-opaque links | Working | — | Non-fatal on failure |
| Internal geocoder | Incident coordinates | Working | — | Local lookup |
| Postgres | Persistence | Working | — |  |

### 2.2 Optional external integrations

Classifications are dev-audit (see Appendix D item E2). Owner may override at sign-off if secrets changed.

| Integration key | Label | M1 classification | Action | Expected API/UI status |
| --- | --- | --- | --- | --- |
| admin_controls | Admin operator controls | Working | Owner (token custody) | configured: true |
| gdelt | GDELT Conflict Events | Intentionally off | Owner | not_configured |
| gdelt_structured | GDELT structured event layer | Intentionally off | Owner | not_configured or disabled |
| reliefweb | ReliefWeb corroboration | Pending | Owner + ReliefWeb | pending |
| reliefweb_reports | ReliefWeb situational reports | Pending | Owner + ReliefWeb | pending |
| liveuamap | Live map overlay | Broken | Owner + Liveuamap | failing_upstream |
| openai | AI prose and headline translation | Intentionally off | Owner | not_configured |
| ais_movement | AIS vessel movement sample | Intentionally off | Owner | not_configured or disabled |
| vessel_registry | Cargo-type vessel lookup | Intentionally off | Owner | disabled |
| social_watch_instagram | KAMMI Instagram OSINT | Intentionally off | Owner | not_configured |
| tapa_iis | TAPA IIS feed | Intentionally off | Owner | N/A (offline) |
| x_cargo_osint | X / cargo OSINT | Intentionally off | Owner | not_configured |

Integration evidence notes

- admin_controls: INGEST_ADMIN_TOKEN set on production. POST /api/admin/ingest without token returned 401 (not 503) on 8 Jul 2026. Changed since June audit when token was unset.

- gdelt / gdelt_structured: No GDELT_CLOUD_API_KEY (June audit). Provision to enable.

- reliefweb / reliefweb_reports: RELIEFWEB_APPNAME not approved; v2 API returns 403 for unapproved appnames.

- liveuamap: LIVEUAMAP_API_KEY present (June audit) but upstream returns 403 on server egress IP. Whitelist or accept off.

- openai: No AI_INTEGRATIONS_OPENAI keys (June audit). Prose route returns 200 with template fallback (no 503).

- ais_movement: Requires AISSTREAM_API_KEY or AIS_API_KEY; free tier covers Asian straits only when on.

- vessel_registry: VESSEL_REGISTRY_ENABLED=false cost kill-switch.

- social_watch_instagram: APIFY_TOKEN optional; manual CLI only.

- tapa_iis: Offline HTML import only; manual admin promote endpoint; not scheduled.

- x_cargo_osint: X_BEARER_TOKEN; manual CLI only.

Dev (M2): Source Health UI must match this table — no false "failing" for intentionally off rows (Appendix B items B1–B4, B10).

### 2.3 Source Health UI honesty (M2 target)

| Issue | Today | M2 fix |
| --- | --- | --- |
| Unconfigured optional integrations show as failures | Partially addressed via not_configured and pending states | Align every row with truth table above |
| ReliefWeb pending vs broken | pending state exists in code | Owner decides: pursue approval or mark intentionally off |
| Liveuamap empty overlay | May look broken without clear message | Clear global "overlay unavailable" if IP blocked |

## 3. Report quality scorecard

Method: Headless PDF export from live database plus in-app editor screenshot from production (Jun 2026). Assessed against customer-demo bar: structurally usable; not sales-demo polished (M4).

Priority products (locked for M4): Country Reports, Shipping, Flashpoint, Fuel

### 3.1 Scorecard

| Product | Sample ID / slug | PDF generated | Layout OK | Maps OK | Tables/charts OK | Preview vs PDF | Result | Quality milestone |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Country | indonesia | Yes | Yes | Yes | Yes | Yes | Fail | M4 |
| Shipping | latest shipping report | Yes | Yes | No | Yes | No | Fail | M4 |
| Flashpoint | latest flashpoint report | Yes | Yes | Yes | Yes | Yes | Fail | M4 |
| Fuel | latest fuel report | Yes | Yes | N/A | Yes | No | Fail | M4 |

Result key: Fail means not customer-demo ready. Export works. Quality fixes are M4.

Sample evidence (Appendix D): E4 country PDF; E3 topic font audit log for shipping, flashpoint, and fuel.

Product notes

- Country: Roboto font audit PASS; per-country bespoke layout; map rasterisation risk.

- Shipping: jsPDF builder path; chokepoint map quality concern.

- Flashpoint: DOM rasterisation generally good; 7-page sample.

- Fuel: jsPDF chart replicas; preview vs PDF parity drift risk.

### 3.2 Cross-cutting PDF issues (code review)

| Issue | Severity | M4 fix |
| --- | --- | --- |
| Multiple export paths (DOM rasterise vs jsPDF builders) | Medium | Parity audit per priority product |
| Font discipline (Roboto only) | Low | Gate exists for country briefs |
| Magic page-break constants | Medium | Any UI change can break PDF pagination |
| Map export quality | Medium | Dedicated print stylesheet or static map snapshot |
| "Data as of" line | OK | Present in preview and headless builders |

### 3.3 Map tool (UI, not PDF)

| Capability | Built? | Gap |
| --- | --- | --- |
| Incident markers by severity | Yes |  |
| Liveuamap overlay | Partial | Upstream / IP dependency |
| Unified filter bar | No | M4 |
| Clustering | No | M4 |
| One-click incident to report builder | No | M4 |
| Export-quality map tiles | No | M4 |

## 4. Workflow gap map

### 4.1 Today (as built)

| Capability | Status | Where |
| --- | --- | --- |
| Report statuses | draft, review, published | topics.ts REPORT_STATUSES |
| Status change | Manual dropdown in editor | No submit/approve actions |
| Due date | Missing | Not in reports schema |
| Owner / assignee | Missing | author field only |
| Review / approval status | Missing | review is not formal approval |
| Export status | Missing |  |
| Distribution status | Missing |  |
| Export PDF gate | None | Any status can export |
| Send / email / WhatsApp | Not implemented |  |
| Version history | Missing |  |
| Event log / audit trail | Missing |  |
| Homepage attention queue | Missing | Dashboard shows KPIs only |
| Report pipeline view | Missing | Flat list with topic/status filter |
| Executive Summary persistence | Partially fixed | DB column exists; legacy localStorage fallback for old reports |

### 4.2 Target (M3 requirements)

| Capability | M3 deliverable |
| --- | --- |
| Status enum | draft, in_review, approved, exported, sent, archived |
| Schema fields | due_date, owner, review_status, approval_status, export_status, distribution_status, approved_at, approved_by, last_edited_at |
| Server rules | Export at approved or later; send at approved plus distribution_status ready |
| UI | Command-centre homepage; report kanban/list; submit for review; approve |
| Audit | report_events table |

### 4.3 Explicitly deferred (not M3)

| Capability | Milestone |
| --- | --- |
| Email distribution lists and templates | M6 |
| WhatsApp share pack | M6 |
| Customer-grade PDF polish | M4 |
| Self-service country/product admin | M5 |

### 4.4 Workflow comparison (today vs target)

| Stage | Today | M3 target | M6 (later) |
| --- | --- | --- | --- |
| Draft | Yes — no gate on PDF export | Yes — submit moves to in_review |  |
| Review | Manual status dropdown only | Formal in_review with approve action |  |
| Approved | Not implemented | Required before export/send | Required before distribution |
| Exported | Not tracked | Tracked status |  |
| Sent / distributed | Not implemented | sent status | Email and WhatsApp share pack (server-gated) |
| Archived | Not implemented | archived status |  |

## 5. Risk register

| ID | Risk | Likelihood | Impact | Owner | Mitigation / M2 action |
| --- | --- | --- | --- | --- | --- |
| R1 | ReliefWeb appname not approved | High | Medium | Owner | Request approval; until then mark Pending or Intentionally off |
| R2 | Liveuamap blocks server egress IP | High | Low–Med | Owner + Liveuamap | IP whitelist request; else clear UI message |
| R3 | INGEST_ADMIN_TOKEN not set | Low | Med | Owner | Resolved since June audit — prod probe shows token configured |
| R4 | OpenAI integration not provisioned | Med | Med | Owner | Add integration OR accept template-only prose (current: 200 response) |
| R5 | GDELT / vessel registry cost overrun | Low | Low | Owner | Keep vessel registry disabled; cap GDELT structured cadence |
| R6 | Preview vs PDF drift on jsPDF topics | Med | High | Dev (M4) | Parity audit Fuel, Shipping, Flashpoint |
| R7 | Boot-time migrations grow fragile | Low | Med | Dev (M2+) | Document; consider drizzle-kit migrations long-term |
| R8 | No approval gate before customer send | High | High | Dev (M3–M6) | Server-enforced workflow before M6 |
| R9 | Executive Summary legacy localStorage | Low | Low | Dev (M3) | Migrate reads to DB-only |
| R10 | Public URL plus owner-only auth | Low | Med | Dev | Replit Auth enforced; unauthenticated API returned 401 (verified 8 Jul 2026) |

## 6. Engineering baseline (context only — not M1 acceptance)

| Metric | Value (July 2026) |
| --- | --- |
| Test files | 80+ under tests/ |
| Typecheck | Clean across workspace packages |
| API contract | OpenAPI to Orval hooks and Zod |
| Auth | Replit Auth; requireOwner on data routes |
| Ingest | runIngestOnce plus advisory lock; automatic scheduler |
| PDF rule | Preview and PDF must not disagree |

Note: June 2026 AUDIT.md stated zero tests — superseded; test suite has since been added.

## Appendix A — Priority order for M3–M6 (locked)

| Rank | Milestone | Cost | Rationale |
| --- | --- | --- | --- |
| 1 | M3 — Command centre and approval workflow | $1,200 | Biggest daily-ops gap; blocks M6 |
| 2 | M4 — Professional reports and PDFs | $1,000 | Customer-demo quality; export gates need M3 |
| 3 | M5 — Country and product expansion | $1,000 | Scale after pipeline and PDF bar proven |
| 4 | M6 — Email and WhatsApp distribution | $800 | Requires approved reports and attachable PDFs |

Hard rule: No automated customer distribution. WhatsApp = share pack (wa.me link plus message plus PDF), not Business API.

Out of scope (full Phase 2): platform rebuild, multi-tenant portal, auto-send, Windward AIS, full no-code product builder.

## Appendix B — M2 fix backlog (numbered, for sign-off)

Pull from this audit. Estimate days are guide only.

| # | Item | Must-fix / Defer | Est. | Acceptance test |
| --- | --- | --- | --- | --- |
| B1 | Source Health reflects admin controls Working (token now set) | Must-fix | 0.5d | Manual ingest 200 with token; UI matches Section 2.2 |
| B2 | ReliefWeb: approve appname OR mark both rows Pending/off in UI | Must-fix | 0.5d | No false failing noise on Source Health |
| B3 | Liveuamap: whitelist IP OR clear overlay-unavailable state | Must-fix | 1d | Map page honest when overlay empty |
| B4 | OpenAI: provision OR confirm template-only prose (already 200) | Must-fix | 0.5d | Country prose 200 with template; UI shows intentionally off |
| B5 | Core route reliability pass | Must-fix | 2d | All routes load; errors user-visible |
| B6 | Ingest scheduler: failures visible in logs and Source Health | Must-fix | 1d | Simulated failure surfaces within one cycle |
| B7 | Loading, empty, and error states on core pages | Must-fix | 2d | No blank screens on API failure |
| B8 | Dashboard fetch bounds if slow on prod | Defer | 1d | Dashboard under 5s with growing incident table |
| B9 | Smoke PDF: Country plus one topic report generates | Must-fix | 0.5d | PDF downloads without error (quality = M4) |
| B10 | Integration status tests pinned | Must-fix | 1d | CI, typecheck, and tests green |
| B11 | Executive Summary: DB persistence; remove legacy localStorage | Defer to M3 | 0.5d | Summary survives cross-browser open |
| B12 | Persist any other localStorage-only editor fields | Defer | 1d | Audit complete |

M2 total (must-fix): approximately 9–10 dev-days (within $1,000 / 10–14 day envelope).

## Appendix C — Owner sign-off

### C.1 M1 Audit Pack acceptance

| Criterion | Met? |
| --- | --- |
| Audit Pack covers live app, sources, report quality, workflow, risks with evidence | Yes (dev audit, prod probes, docs/m1-evidence/) |
| Every source row classified: Working, Intentionally off, Broken, or Pending | Yes (Sections 2.1 and 2.2) |
| One sample PDF assessed per priority product with pass/fail notes | Yes (Section 3.1) |
| Workflow gap doc: today vs M3; distribution deferred to M6 | Yes (Section 4) |
| Priority order M3–M6 signed off | Pending — Owner |
| M2 backlog agreed with acceptance tests | Pending — Owner |

### C.2 Sign-off

| Role | Name | Signature | Date |
| --- | --- | --- | --- |
| Owner |  |  |  |
| Developer | Tommy To | Tommy | 2026-07-09 |

Revision round: One included in M1.

Notes:

## Appendix D — Evidence index

| # | Artifact | Location | Status |
| --- | --- | --- | --- |
| E1 | Report editor and PDF preview (production) | docs/m1-evidence/screenshots/routes/05-reports-editor.png | Dev audit |
| E2 | Integration classification basis | docs/m1-evidence/exports/E3-integration-classification-basis.md | Dev audit |
| E3 | Topic PDF font audit (shipping, fuel, flashpoint) | docs/m1-evidence/exports/E3-topic-pdf-font-audit.txt | Dev audit |
| E4 | Sample PDF — Country (Indonesia) | docs/m1-evidence/pdfs/E4-country-indonesia.pdf | Dev audit |
| E5 | Sample PDF — Shipping (font audit reference) | E3 log references shipping_report.pdf | Dev audit |
| E6 | Sample PDF — Flashpoint (font audit reference) | E3 log references flashpoint_report.pdf | Dev audit |
| E7 | Sample PDF — Fuel (font audit reference) | E3 log references fuel_report.pdf | Dev audit |
| E8 | Prior workbench audit | docs/workbench-audit-2026-06-17.md | In repo |
| E9 | Phase 2 commercial proposal | Phase 2 Proposal.docx | In repo |
| E10 | Auth — unauthenticated API blocked | Section 1.2 — GET /api/incidents returned 401 (8 Jul 2026) | Prod |
| E11 | Health check public | Section 1.2 — GET /api/healthz returned 200 (8 Jul 2026) | Prod |
| E12 | Admin token configured | Section 1.3 — POST /api/admin/ingest no token returned 401 (8 Jul 2026) | Prod |

End of M1 Audit Pack. Owner signs Appendix C to lock priority order and start M2.